## Sheet1
Task | User Story | Time Estimation
Research: look for chat frameworks compatible with Angular/NodeJS | Real-time chat | 4h
Research: look for notifications frameworks compatible with Angular/NodeJS | Notifications | 4h
Redirect to login page on refresh (FE bug) | Bug fixing | 4h
Profile errors when switching pages | Bug fixing | 3h
Unauthenticated users can navigate to post/profile by URL | Bug fixing | 2h
Slow feed loading (FE + BE) | App improvements | 6h
Use following flag in database to toggle profile visibility if profile is set to private | Private profile | 6h
Endpoint for post pagination | App improvements | 6h
Enhanced ordering of posts shown on main feed | UX | 24h
Research: Find suitable machine learning models and tools | Recommender system | 1 week
Interface that gets toggled when user signs in as admin | Admin dashboard | 1 week